## Sheet1
Month | Jan | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun
Week | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Planning Report
Modelling
Data Collection
Data Processing
Tuning and Validation
Testing and Evaluation
Report Writing | [13 empty] | Draft |  |  |  | Finished
Opposition
Presentation